## Responsibilities
Phase |  |  | Workpackage |  |  | SAP | [11 empty] | Eco Ltd. | [11 empty] | Partner
| Topic Area | Activity |  | Deliverable | Date | Steering Committee (Mr.XXXX) | Program Management (Mrs. YYYY) | Program Office (Mr.XX) | Project Management (Mr.HHHHH) | Integration Team (Mr.Buasch) | KM-Team (Mrs.EEEE) | Usermanagement-Team (Mr.Beth) | Security-Team (Mr.Beth) | Content-Team (Mr.Isch) | Infrastucture-Team (Mr.Sekier) | Technology-Team (Hr.Sekier) | Operations-Team (Mr.Schmid) | Steering Committee (´Mrs.Lone) | Program Management (Mr.Jon) | Program Office (Mr.Carl) | Project Management (Mr.Jon) | Integration Team (Mr.Zzzz) | KM-Team (Mr.Zzzz) | Usermanagement-Team (Mr.Zzzz) | Security-Team (Mr.Newman) | Content-Team (Mrs.Pysch) | Infrastucture-Team (Mr.Mysam) | Technology-Team (Mr.Sen) | Operations Team (Mr.Sen) | Project Lead Documentum (Mr.Norb) | Project Lead Novell | Project Lead (Mr.Hylstenhill)
Project Management |  |  | A1.1
Project Organisation
Communication
Project Controlling
|  | Reporting Level I |  | Progress Report
|  | Reporting Level II |  | Progress Report
|  | Reporting Level III |  | Progress Report
|  | Reporting Level IV |  | Progress Report
| Change Request Procedure |  | A1.2
Risk Management
Project Standards
Project Preparation
Projekt Charter
Quality Management
Review process
Training Project Team
Business Blueprint
Infrastructure
Knowledge Management
Usermanagement
Security
Content
Technology
Realization
Infrastructure
Knowledge Management
Usermanagement
Security
Content
Technology
Governance
Final Preparation
Enduser Training
System Tests
Safeguarding
Go-Live & Support
| GoLive Phase 1 Portal Platform |  |  |  | 2003-07-15
| GoLive Phase 2 Knowledge Management |  |  |  | 2003-09-26
| GoLive Phase 3 Collaboration |  |  |  | 2003-12-22
| Project End |  |  |  | 2003-12-31
[33 empty] | responsible | v
[33 empty] | collaborate | m
[33 empty] | to be informed | i
[33 empty] | review | r
[33 empty] | approval | a