## Overview Users
EP AIM
Date | Total Cumulative No. of Users | Users in AP | Users in EU
2003-02-20 | 10 | 0 | 10
2003-03-02 | 170 | 0 | 170
2003-03-15 | 230 | 0 | 230
2003-04-01 | 1200 | 0 | 1200
EP So36
Date | Total Cumulative No. of Users | Users in AP | Users in EU
31st Mar. 03 | 60 | 55 | 5
30th Jun. 03 | 120 | 115 | 5
30th Sept. 03 | 240 | 235 | 5
31st Dec. 03 | 400 | 390 | 10
31st Mar. 04 | 700 | 690 | 10
30th Jun. 04 | 850 | 840 | 10
30th Sept. 04 | 950 | 940 | 10
31st Dec. 04 | 1000 | 990 | 10
EP ANLA
Date | Total Cumulative No. of Users | Users in AP | Users in EU
2003-05-10 | 225? | 0 | 225

## Overview Users EU Cluster
EU Cluster
Date/Users | 100 | 200 | 300 | 400 | 500 | 600 | 700 | 800 | 900 | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700 | 1800 | 1900 | 2000
2003-01-01
2003-02-01 | 100
2003-03-01 | 5 | [10 empty] | 1200
2003-04-01
2003-05-01 |  |  | 225 | [10 empty] | 1400
2003-06-01 | 10 | [16 empty] | 1560
2003-07-01 | [18 empty] | 1660
2003-08-01
2003-09-01 | 15
2003-10-01
2003-11-01
2003-12-01 | 25
2004-01-01
2004-02-01
2004-03-01
2004-04-01
2004-05-01
2004-06-01
2004-07-01
2004-08-01
2004-09-01
2004-10-01
2004-11-01
2004-12-01
Content
EPOne
Blueprint Academy
SOPE
SCITe

## ServiceContent AIM
| Content Development |  |  |  |  | Content Acceptance |  |  |  |  | Content Deployment | [5 empty] | 520 | 511 | 514
AIM Content | Content requirements defined | User acceptance of requirements | Content developed | Content debugged | User acceptance tests | Code review regarding development standards | Check for compliance with content standards | Portfolio acceptance | Content loaded on acceptance | Load scripts developed | Deployment targets for content defined | Deployment planned | Deployment executed | Deployment result user tested on production | Deployment stress tested on production | Deployment result accepted by owners of content | AIM YYYY | Assessment | Production | Remarks
Federate Search Framework
Factiva search
Google search
Google search API Java solution
Livelink search
SWW search
Sitescape search
W=W search
Livelink 4.5 interface
Livelink Enterprise workspace
Livelink project workspace
Livelink personal workspace
Livelink personal projects
Livelink Enhancements
Livelink Multiple Instance NTLM
CPI (connection Pool)
Livelink Teamroom
List of my teams
Startup open
Search
workspaces
Enterprise news
caching mechanism for enterprise (version 2)
Selection coordinator / member for teams and projects
Selection home instance / all instance (version 2)
Handle projects as virtual teams
last changed (my recent documents) (Version 2)
Present sorted listst for teams and projects alphabetically
Sort by team name and last changed (version 2)
Pop up window with navigator (2 levels) works with folder, project and virtual team
Support for discussions version 2)
Support for required attributes (add view, documents) version 2)
Classic interface Button Radio
Search across my teams , enterpise, personal, my projects
Works for selected en all of my teams (version 3)
Rename function in actions
Add document name for saving (version 2)
Multiple select move and copy (version 2)
Name user under e-mail message (version 2)
display content default sort first folders then documents
My favorites (if available only for teams, folders, projects)
Code review
NTLM / Kerberos authentication
Sitescape Alerts & Queries (10)
Outlook
Outlook client all in one
Outlook calendar
Outlook in box
Outlook sent
Outlook notes
Outlook Tasks
BBC News
BBC weather
CNN news
CNN Oilprices
Factiva.com
Worldclock
Note on A55: Registered User: No global contract has been signed. Piggy bag contract will be signed for Factiva.com
Note on A56: Registered User: No global contract has been signed. Piggy bag contract will be signed for Factiva.com
Note on A57: Registered User: No global contract has been signed. Piggy bag contract will be signed for Factiva.com
Note on A58: Registered User: No global contract has been signed. Piggy bag contract will be signed for Factiva.com
Note on A59: Registered User: Contract requested by Geert K. and
Note on A60: Registered User: Initial design by CMG, possible further development on status bar possible